## Sheet1
Phase 1: Planning & Setup (Week 1)
✅ Select a Use Case: (Team Discussion & Consensus)
✅ Assign Equal Responsibility Areas to Each Developer
✅ Setup Project Repository & Collaboration Workflow
✅ Prepare Dataset Processing Pipeline
Phase 2: Model Development & Experimentation (Week 2-3)
✅ Build ML Model & Experiment with Hyperparameter Tuning
✅ Implement Training, Prediction & Best Model Selection
✅ Log experiments using MLFlow
✅ REST API development
Phase 3: Deployment & Documentation (Week 4)
✅ Create Docker Container for REST API & MLFlow
✅ Push Docker Image to Docker Hub
✅ Prepare Final Report & Presentation
Project Deliverables:
✔ Working ML Model (Logged in MLFlow)
✔ REST API (Training, Prediction, Best Model)
✔ Dockerized Application (MLFlow UI + REST API)
✔ GitHub Repository with Equal Contributions
✔ Final Presentation & Documentation

## Sheet2
Task Distribution:
Sanjeev | Setup GitHub repository, branching strategy & issue tracking | Done
Akshada | Research & define model selection strategy (BERT, TF-IDF, Ensemble, etc.) | Done
Radhika | Data preprocessing & augmentation strategy | WIP
Ruturaj | Setup MLFlow for experiment tracking
Sanjeev | Model Training & Hyperparameter Tuning (logging runs with MLFlow)
Akshada | API Development (GET & POST methods for training, prediction)
Radhika | Model Evaluation & Best Model Selection
Ruturaj | Experiment Logging, Code Optimization & Debugging
Sanjeev | Dockerfile & containerization of ML model API
Akshada | Integration of MLFlow UI in Docker setup
Radhika | Deployment Testing & Bug Fixes
Ruturaj | Documentation (README, API Endpoints, How-to-run guide)